## Sheet1_2
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
WP1: Project Management & Coordination
T1.1 Project implementation plan and Project Management Board (M1-M36): Lead NTUA
T1.2 Quality management and monitoring (M1-M36): Lead CLS
T1.3 Risk management (M1-M36): Lead GFZ
T1.4 Financial management (M1-M36); Lead NTUA
T1.5 Coordination, communication and administration (M1-M36); Lead NTUA
WP2: Transfer of knowledge
T2.1 Transfer of knowledge for DORIS					D2.1
T2.2 Transfer of knowledge for SLR					D2.2
T2.3 Transfer of knowledge for VLBI					D2.3
T2.4 Assessment of currently available software tools					D2.1
T2.5 Attending training events					D2.5
WP3: Building Excellence Capacity
T3.1 Building research capacity via DORIS					D3.1
T3.2 Building research capacity via SLR					D3.2
T3.3 Building research capacity via VLBI					D3.3
T3.4 Long term plan for scientific excellence
WP4: Strengthening research management, administration and funding capacity
T4.1 Establish a research management/administration unit in the Coordinator institute				D4.1
T4.2 Strengthening research management capacity and administrative skills
T4.3 Exploring funding pools and opportunities					D4.2
T4.4 Enhancing research funding capacity					D4.3					D4.3
WP5: Networking and Ecosystem Activities
T5.1 Agreement on PhD and PostDoc co-supervision				D5.1

T5.3 Establishing a Greek Ecosystem of partners in space-based geosciences					D5.2
T5.4 Exploring Greek academia needs and interest in Space Geodesy					D5.3
T5.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP6: Dissemination, Exploitation and Communication
T6.1 Project website and social media engagement					D6.1
T6.2 Sharing of technical knowledge and know-how					D6.3
T6.3 Joint Summer School					D6.6
T6.4 Open-Access publications
T6.5 Dissemination activities and support for the Greek ecosystem					D6.4					D6.5
T6.6 Approaching high-schools students and the Greek STEM community
T6.7 ARONYM Newsletter					D6.2					D6.2					D6.2					D6.2					D6.2

## Sheet1_2_2
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
	Reporting Period (RP1)					Reporting Period (RP2)
WP1: Project Management & Coordination (RP1)
T1.1 Project implementation plan and Project Management Board
T1.2 Quality management and monitoring
T1.3 Risk management
T1.4 Financial management
T1.5 Coordination, communication and administration
WP2: Project Management & Coordination (RP2)
T2.1 Project implementation plan and Project Management Board
T2.2 Quality management and monitoring
T2.3 Risk management
T2.4 Financial management
T2.5 Coordination, communication and administration
WP3: Transfer of knowledge
T3.1 Transfer of knowledge for DORIS					D2.1
T3.2 Transfer of knowledge for SLR					D2.2
T3.3 Transfer of knowledge for VLBI					D2.3
T3.4 Attending training events					D2.5
T3.5 Assessment of currently available software tools					D2.1
WP4: Building Excellence Capacity (RP1)
T4.1 Building research capacity via DORIS					D3.1
T4.2 Building research capacity via SLR					D3.2
T4.3 Building research capacity via VLBI					D3.3
T4.4 Attending training events
WP5: Building Excellence Capacity (RP2)
T5.1 Building research capacity via DORIS
T5.2 Building research capacity via SLR
T5.3 Building research capacity via VLBI
T5.4 Attending training events
T5.4 Long term plan for scientific excellence
WP6: Strengthening research management, administration and funding capacity
T6.1 Establish a research management/administration unit in the Coordinator institute				D4.1
T6.2 Exploring funding pools and opportunities
T6.3 Strengthening research management capacity and administrative skills					D4.2
T6.4 Enhancing research funding capacity					D4.3
WP7: Networking and Ecosystem Activities
T7.1 Agreement on PhD and PostDoc co-supervision				D5.1

T7.3 Establishing a Greek Ecosystem of partners in space-based geosciences					D5.2
T7.4 Exploring Greek academia needs and interest in Space Geodesy					D5.3
T7.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP8: Dissemination, Exploitation and Communication (RP1)
T8.1 Project website and social media engagement					D6.1
T8.2 Sharing of technical knowledge and know-how					D6.3
T8.3 Open-Access publications
T8.4 Approaching high-schools students and the Greek STEM community
T8.5 ARONYM Newsletter					D6.2					D6.2
WP9: Dissemination, Exploitation and Communication (RP2)
T9.1 Project website and social media engagement
T9.2 Sharing of technical knowledge and know-how
T9.3 Open-Access publications
T9.4 Approaching high-schools students and the Greek STEM community
T9.5 ARONYM Newsletter					D6.2					D6.2					D6.2
T9.6 Dissemination activities and support for the Greek ecosystem
T9.7 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School