## gantt
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
	Reporting Period (RP1)					Reporting Period (RP2)
WP1: Project Management & Coordination (RP1)				D1.1		D1.2					D1.2					D1.2					D1.2					D1.2
T1.1 Project implementation plan and Project Management Board
T1.2 Quality management and monitoring
T1.3 Risk management
T1.4 Financial management
T1.5 Coordination, communication and administration
WP2: Project Management & Coordination (RP2)					D2.1
T2.1 Project implementation plan and Project Management Board
T2.2 Quality management and monitoring
T2.3 Risk management
T2.4 Financial management
T2.5 Coordination, communication and administration
WP3: Transfer of knowledge					D3.1	D3.2, D3.3, D3.4
T3.1 Transfer of knowledge for DORIS
T3.2 Transfer of knowledge for SLR
T3.3 Transfer of knowledge for VLBI
T3.4 Attending training events
T3.5 Assessment of currently available software tools
WP4: Building Excellence Capacity (RP1)
T4.1 Building research capacity via DORIS
T4.2 Building research capacity via SLR
T4.3 Building research capacity via VLBI
T4.4 Attending training events
WP5: Building Excellence Capacity (RP2)					D5.1,D5.2,D5.3,D5.4,D5.5
T5.1 Building research capacity via DORIS
T5.2 Building research capacity via SLR
T5.3 Building research capacity via VLBI
T5.4 Attending training events
T5.5 Long term plan for scientific excellence
WP6: Strengthening research management, administration and funding capacity			D6.1					D6.2					D6.3
T6.1 Establish a research management/administration unit in the Coordinator institute
T6.2 Exploring funding pools and opportunities
T6.3 Strengthening research management capacity and administrative skills
T6.4 Enhancing research funding capacity
WP7: Networking and Ecosystem Activities				D7.1					D7.2					D7.3, D7.4
T7.1 Agreement on PhD and PostDoc co-supervision
T7.2 Exploring roles and prescriptive in Space Geodetic International Services and Consortia
T7.3 Establishing a Greek Ecosystem of partners in space-based geosciences
T7.4 Exploring Greek academia needs and interest in Space Geodesy
T7.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP8: Dissemination, Exploitation and Communication (RP1)					D8.1, D8.2					D8.2					D8.2					D8.2					D8.2
T8.1 Project website and social media engagement
T8.2 Sharing of technical knowledge and know-how
T8.3 Open-Access publications
T8.4 Approaching high-schools students and the Greek STEM community
T8.5 ARONYM Newsletter
WP9: Dissemination, Exploitation and Communication (RP2)					D9.1					D9.2					D9.3, D9.4,D9.5
T9.1 Project website and social media engagement
T9.2 Sharing of technical knowledge and know-how
T9.3 Open-Access publications
T9.4 Approaching high-schools students and the Greek STEM community
T9.5 ARONYM Newsletter
T9.6 Dissemination activities and support for the Greek ecosystem
T9.7 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School

## gantt_nod
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
	Reporting Period (RP1)					Reporting Period (RP2)
WP1: Project Management & Coordination (RP1)
T1.1 Project implementation plan and Project Management Board
T1.2 Quality management and monitoring
T1.3 Risk management
T1.4 Financial management
T1.5 Coordination, communication and administration
WP2: Project Management & Coordination (RP2)
T2.1 Project implementation plan and Project Management Board
T2.2 Quality management and monitoring
T2.3 Risk management
T2.4 Financial management
T2.5 Coordination, communication and administration
WP3: Transfer of knowledge
T3.1 Transfer of knowledge for DORIS
T3.2 Transfer of knowledge for SLR
T3.3 Transfer of knowledge for VLBI
T3.4 Attending training events
T3.5 Assessment of currently available software tools
WP4: Building Excellence Capacity (RP1)
T4.1 Building research capacity via DORIS
T4.2 Building research capacity via SLR
T4.3 Building research capacity via VLBI
T4.4 Attending training events
WP5: Building Excellence Capacity (RP2)
T5.1 Building research capacity via DORIS
T5.2 Building research capacity via SLR
T5.3 Building research capacity via VLBI
T5.4 Attending training events
T5.5 Long term plan for scientific excellence
WP6: Strengthening research management, administration and funding capacity
T6.1 Establish a research management/administration unit in the Coordinator institute
T6.2 Exploring funding pools and opportunities
T6.3 Strengthening research management capacity and administrative skills
T6.4 Enhancing research funding capacity
WP7: Networking and Ecosystem Activities
T7.1 Agreement on PhD and PostDoc co-supervision
T7.2 Exploring roles and prescriptive in Space Geodetic International Services and Consortia
T7.3 Establishing a Greek Ecosystem of partners in space-based geosciences
T7.4 Exploring Greek academia needs and interest in Space Geodesy
T7.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP8: Dissemination, Exploitation and Communication (RP1)
T8.1 Project website and social media engagement
T8.2 Sharing of technical knowledge and know-how
T8.3 Open-Access publications
T8.4 Approaching high-schools students and the Greek STEM community
T8.5 ARONYM Newsletter
WP9: Dissemination, Exploitation and Communication (RP2)
T9.1 Project website and social media engagement
T9.2 Sharing of technical knowledge and know-how
T9.3 Open-Access publications
T9.4 Approaching high-schools students and the Greek STEM community
T9.5 ARONYM Newsletter
T9.6 Dissemination activities and support for the Greek ecosystem
T9.7 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School

## gender
NTUA	3	7	42.9
OSO	2	4	50.0
CLS	1	3	33.3
IPGP	2	5	40.0
GFZ	1	5	20.0
	9	24	37.5

## gantt_2
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
	Reporting Period (RP1)					Reporting Period (RP2)
WP1: Project Management & Coordination (RP1)				D1.1		D1.2					D1.2					D1.2					D1.2					D1.2
T1.1 Project implementation plan and Project Management Board
T1.2 Quality management and monitoring
T1.3 Risk management
T1.4 Financial management
T1.5 Coordination, communication and administration
WP2: Project Management & Coordination (RP2)					D2.1
T2.1 Project implementation plan and Project Management Board
T2.2 Quality management and monitoring
T2.3 Risk management
T2.4 Financial management
T2.5 Coordination, communication and administration
WP3: Transfer of knowledge					D3.1	D3.2, D3.3, D3.4
T3.1 Transfer of knowledge for DORIS
T3.2 Transfer of knowledge for SLR
T3.3 Transfer of knowledge for VLBI
T3.4 Attending training events
T3.5 Assessment of currently available software tools
WP4: Building Excellence Capacity (RP1)
T4.1 Building research capacity via DORIS
T4.2 Building research capacity via SLR
T4.3 Building research capacity via VLBI
T4.4 Attending training events
WP5: Building Excellence Capacity (RP2)					D5.1,D5.2,D5.3,D5.4,D5.5
T5.1 Building research capacity via DORIS
T5.2 Building research capacity via SLR
T5.3 Building research capacity via VLBI
T5.4 Attending training events
T5.5 Long term plan for scientific excellence
WP6: Strengthening research management, administration and funding capacity			D6.1					D6.2					D6.3
T6.1 Establish a research management/administration unit in the Coordinator institute
T6.2 Exploring funding pools and opportunities
T6.3 Strengthening research management capacity and administrative skills
T6.4 Enhancing research funding capacity
WP7: Networking and Ecosystem Activities				D7.1					D7.2					D7.3, D7.4
T7.1 Agreement on PhD and PostDoc co-supervision
T7.2 Exploring roles and prescriptive in Space Geodetic International Services and Consortia
T7.3 Establishing a Greek Ecosystem of partners in space-based geosciences
T7.4 Exploring Greek academia needs and interest in Space Geodesy
T7.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP8: Dissemination, Exploitation and Communication (RP1)					D8.1, D8.2					D8.2					D8.2					D8.2					D8.2
T8.1 Project website and social media engagement
T8.2 Sharing of technical knowledge and know-how
T8.3 Open-Access publications
T8.4 Approaching high-schools students and the Greek STEM community
T8.5 ARONYM Newsletter
WP9: Dissemination, Exploitation and Communication (RP2)					D9.1					D9.2					D9.3, D9.4,D9.5
T9.1 Project website and social media engagement
T9.2 Sharing of technical knowledge and know-how
T9.3 Open-Access publications
T9.4 Approaching high-schools students and the Greek STEM community
T9.5 ARONYM Newsletter
T9.6 Dissemination activities and support for the Greek ecosystem
T9.7 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School					T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School	T6.3 Joint Summer School