## Sheet1
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
WP2: Transfer of knowledge
T2.1 Transfer of knowledge for DORIS
T2.2 Transfer of knowledge for SLR
T2.3 Transfer of knowledge for VLBI
T2.4 Assessment of currently available software tools
T2.5 Attending training events
WP3: Building Excellence Capacity
T3.1 Building research capacity via DORIS
T3.2 Building research capacity via SLR
T3.3 Building research capacity via VLBI
T3.4 Long term plan for scientific excellence
WP4: Strengthening research management, administration and funding capacity
T4.1 Establish a research management/administration unit in the Coordinator institute
T4.2 Strengthening research management capacity and administrative skills
T4.3 Exploring funding pools and opportunities
T4.4 Enhancing research funding capacity
WP5: Networking and Ecosystem Activities
T5.1 Agreement on PhD and PostDoc co-supervision

T5.3 Establishing a Greek Ecosystem of partners in space-based geosciences
T5.4 Exploring Greek academia needs and interest in Space Geodesy
T5.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP6: Dissemination, Exploitation and Communication
T6.1 Project website and social media engagement
T6.2 Sharing of technical knowledge and know-how
T6.3 Joint Summer School
T6.4 Open-Access publications
T6.5 Dissemination activities and support for the Greek ecosystem
T6.6 Approaching high-schools students and the Greek STEM community
T6.7 ARONYM Newsletter

## Sheet1_2
	Year 1					Year 2					Year 3
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
WP2: Transfer of knowledge
T2.1 Transfer of knowledge for DORIS					D2.1
T2.2 Transfer of knowledge for SLR					D2.2
T2.3 Transfer of knowledge for VLBI					D2.3
T2.4 Assessment of currently available software tools					D2.1
T2.5 Attending training events					D2.5
WP3: Building Excellence Capacity
T3.1 Building research capacity via DORIS					D3.1
T3.2 Building research capacity via SLR					D3.2
T3.3 Building research capacity via VLBI					D3.3
T3.4 Long term plan for scientific excellence
WP4: Strengthening research management, administration and funding capacity
T4.1 Establish a research management/administration unit in the Coordinator institute				D4.1
T4.2 Strengthening research management capacity and administrative skills
T4.3 Exploring funding pools and opportunities					D4.2
T4.4 Enhancing research funding capacity					D4.3					D4.3
WP5: Networking and Ecosystem Activities
T5.1 Agreement on PhD and PostDoc co-supervision				D5.1

T5.3 Establishing a Greek Ecosystem of partners in space-based geosciences					D5.2
T5.4 Exploring Greek academia needs and interest in Space Geodesy					D5.3
T5.5 Exploring stakeholders and commercial needs and interest in Space Geodesy
WP6: Dissemination, Exploitation and Communication
T6.1 Project website and social media engagement					D6.1
T6.2 Sharing of technical knowledge and know-how					D6.3
T6.3 Joint Summer School					D6.6
T6.4 Open-Access publications
T6.5 Dissemination activities and support for the Greek ecosystem					D6.4					D6.5
T6.6 Approaching high-schools students and the Greek STEM community
T6.7 ARONYM Newsletter					D6.2					D6.2					D6.2					D6.2					D6.2